## cs-160-mime-101-fin
CS 160 / MIME 101 Final Timeline
Administrative
Name | Person | Status | Timeline - Start | Timeline - End | Deadline | Progress
Establish timeline of milestones and requirements |  | Done | 2018-11-05 | 2018-11-06 | 2018-11-06 | 100%
Schedule times to meet |  | Done | 2018-11-05 | 2018-11-06 | 2018-11-06 | 100%
Attend check-in meetings |  | Working on it | 2018-11-07 | 2018-11-25 |  | 0%
Mid-implementation check-in of progress, supporting each other (fresh eyes on our individual work) |  | Not started | 2018-11-15 | 2018-11-17 |  | 0%
Final check-in of individual tasks |  | Not started | 2018-11-20 | 2018-11-22 | 2018-11-22 | 0%
40%
Program Design and Implementation
Name | Person | Status | Timeline - Start | Timeline - End | Deadline | Progress
Understand problem | Nicholas Olson | Done | 2018-11-06 | 2018-11-06 | 2018-11-06 | 100%
Draft out requirements and possible solutions | Nicholas Olson | Done | 2018-11-07 | 2018-11-07 | 2018-11-07 | 100%
Explore options for implementaion (ev3dev's validity / feasibility) | Nicholas Olson | Done | 2018-11-07 | 2018-11-07 | 2018-11-07 | 100%
Devise a plan and formulate pseudocode for approaches | Nicholas Olson | Done | 2018-11-08 | 2018-11-09 | 2018-11-09 | 100%
Establish testing plan for individual functions and for overall process | Nicholas Olson | Working on it | 2018-11-08 | 2018-11-09 | 2018-11-09 | 0%
Implement plan in Python / Mindstorms' awful interface: | Nicholas Olson | Not started | 2018-11-10 | 2018-11-13 | 2018-11-13 | 0%
'-----------Implement functions for searching, driving, checking color of a pill, checking color of a container, etc. | Nicholas Olson | Not started | 2018-11-10 | 2018-11-12 | 2018-11-12 | 0%
'-----------Implement overall flow of program, connecting functions to pull functions together | Nicholas Olson | Not started | 2018-11-13 | 2018-11-13 | 2018-11-13 | 0%
50%
Program Testing & Finalization
Name | Person | Status | Timeline - Start | Timeline - End | Deadline | Progress
Debug / test implementation: | Nicholas Olson | Not started | 2018-11-14 | 2018-11-19 | 2018-11-19 | 0%
'-----------First check of functionality on ev3 robot | Nicholas Olson | Not started | 2018-11-14 | 2018-11-14 |  | 0%
'----------------------Test implementation of individual functions in lab or lab after-hours | Nicholas Olson | Not started |  |  |  | 0%
'----------------------Test implementation with test-run using competition set-up, if possible | Nicholas Olson | Not started |  |  |  | 0%
'----------------------Revise implementation as needed | Nicholas Olson | Not started | 2018-11-15 | 2018-11-16 |  | 0%
'-----------Second chance to test functions, repeating sub-steps | Nicholas Olson | Not started | 2018-11-17 | 2018-11-17 |  | 0%
'----------------------Re-test implementation of individual functions in lab or lab after-hours | Nicholas Olson | Not started |  |  |  | 0%
'----------------------Re-Test implementation with test-run using competition set-up, if possible | Nicholas Olson | Not started |  |  |  | 0%
'----------------------Revise implementation as needed | Nicholas Olson | Not started | 2018-11-18 | 2018-11-19 |  | 0%
Finalize implementation, check-in with partner one last time | Nicholas Olson | Not started | 2018-11-20 | 2018-11-21 |  | 0%
Reflect on process, journal on reflection | Nicholas Olson | Not started | 2018-11-21 | 2018-11-21 | 2018-11-21 | 0%
0%
Technical Design & Actualization
Name | Person | Status | Timeline - Start | Timeline - End | Deadline | Progress
Determine dimensions of the pills (vital information) | Ty Brewen | Working on it | 2018-11-07 | 2018-11-11 |  | 0%
Complete conceptual design of overall system | Ty Brewen | Done | 2018-11-07 | 2018-11-10 | 2018-11-10 | 100%
Design and perfect gear and motor relationships | Ty Brewen | Not started | 2018-11-11 | 2018-11-14 | 2018-11-14 | 0%
Create rough schematic of the robot from the top and side | Ty Brewen | Done | 2018-11-07 | 2018-11-10 | 2018-11-10 | 100%
Integrate systems together and determine measurements for 3D modeled parts | Ty Brewen | Not started | 2018-11-08 | 2018-11-11 | 2018-11-16 | 0%
Design all 3D printed parts needed for overall system | Ty Brewen | Not started | 2018-11-11 | 2018-11-15 | 2018-11-15 | 0%
Order 3D printed parts | Ty Brewen | Not started | 2018-11-15 | 2018-11-16 | 2018-11-16 | 0%
Construct draft of design during lab or after-hours | Ty Brewen | Not started | 2018-11-19 | 2018-11-20 | 2018-11-20 | 0%
Test the design for errors during lab or after-hours | Ty Brewen | Not started | 2018-11-19 | 2018-11-21 | 2018-11-21 | 0%
Adjust model and its technical solutions, accounting for errors | Ty Brewen | Not started | 2018-11-21 | 2018-11-22 | 2018-11-22 | 0%
Construct final design during lab or after-hours | Ty Brewen | Not started | 2018-11-22 | 2018-11-25 | 2018-11-25 | 0%
Test final design for new or repeated issues | Ty Brewen | Not started | 2018-11-24 | 2018-11-25 | 2018-11-25 | 0%
17%
Report
Name | Person | Status | Timeline - Start | Timeline - End | Deadline | Progress
Outline final report (before any implementation, keeping notes as we go) |  | Not started | 2018-11-10 | 2018-11-10 | 2018-11-10 | 0%
Research real-world equivalents to the problem and possible solutions to the problem |  | Not started | 2018-11-11 | 2018-11-11 | 2018-11-11 | 0%
Compile / draft each section of the final as they become possible during overall process |  | Not started | 2018-11-12 | 2018-11-21 |  | 0%
Draft final report |  | Not started | 2018-11-22 | 2018-11-23 | 2018-11-23 | 0%
Revise final report |  | Not started | 2018-11-24 | 2018-11-24 | 2018-11-24 | 0%
Finalize final report |  | Not started | 2018-11-25 | 2018-11-25 | 2018-11-25 | 0%
Turn in final report |  | Not started | 2018-11-25 | 2018-11-25 | 2018-11-25 | 0%
0%